## INTRO
BIM MODEL CONTENT - LEVEL OF DEVELOPMENT MATRIX |  |  |  |  | 2018
Project Name |  |  |  |  | Date
GOAL: | This worksheet was developed to aid the project team to define the BIM content LOD required to implement each BIM Use with maximum efficiency.
NOTE: This worksheet is a guide for the project team to define model creation scope of work and model level of development. Please review the Level of Development (LOD) definitions. The LOD will aid in determining the level of involvement of the project stakeholders from design through facility turnover. This worksheet is intended to guide the project team in achieving project goals, accomodate required BIM uses, and meet schedule requirements for the project. This worksheet will be used to audit BIM progress throughout the project and to coordinate work efforts.
Level of Development (LOD) is the level of completeness to which a model element is developed at the end of each project phase.
LOD 100: | The model element may be graphically represented in the Model with a symbol or other generic representation, but does not satisfy the requirements for LOD 200. Information related to the Model Element (i.e. cost per square foot, tonnage of HVAC, etc.) can be derived from other Model Elements. The basic size, shape, and position of the element being modeled can be considered accurate. At this stage, most objects and embedded parameters are considered temporary and will be revised as the design evolves and more specific information is identified.
Schematic Design; overall building massing; whole building analysis (volume, orientation, square footage costs)
LOD 200: | The model element is graphically represented within the Model as a generic system, object, or assembly with approximate quantities, size, shape, location, and orientation. Non-graphic information may also be attached to the Model Element. This includes more developed geometry which makes apparent what the element is by visual image. This also includes proper location in relationship to adjacent elements. Specific information needed about the object relative to its design intent begins to be inputted.
Design Development; generalized systems/assemblies (approximate quantities, size, shape, location, orientation); selected system performance analysis
LOD 300: | The model element is graphically represented within the Model as a specific system, object or assembly in terms of quantity, size, shape, location, and orientation. Non-graphic information may also be attached to the Model Element. This includes all object geometry, location, size, type and specifications of an object to communicate design intent for proper documentation and construction. At this point all information about these objects should be considered reliable to generate construction documents.
Construction Documentation; generation of traditional CD's and shop drawings; analysis and simulation of detailed elements/systems; includes attributes and parameters defined by SI
LOD 350: | The model element is graphically represented within the Model as a specific system, object, or assembly in terms of quantity, size, shape, orientation, and interfaces with other building systems. Non-graphic information may also be attached to the Model Element. A 350 level LOD would define model elements sufficiently developed to enable coordination between disciplines – e.g. clash detection/avoidance, layout, etc. The requirements for this level are higher than those for 300, but not as high as those for 400, thus it was designated as LOD 350.
Construction Documentation; generation of traditional CD's and shop drawings; analysis and simulation of detailed elements/systems; includes attributes and parameters defined by SI
LOD 400: | The model element is graphically represented within the Model as a specific system, object or assembly in terms of size, shape, location, quantity, and orientation with detailing, fabrication, assembly, and installation information. Non-graphic information may also be attached to the Model Element.
Construction Adiminstration/Shop Drawings; includes specific assemblies which are accurate in terms of quantity, size, shape, location, and orientation; virtual representations of the proposed elements, suitable for construction, fabirication, and assembly
LOD 500: | The model element is a field verified representation in terms of size, shape, location, quantity, and orientation. Non-graphic information may also be attached to the Model Elements.
Project Completion/Record Drawings/As-built Conditions; model is configured to be the central data storage for integration into the building maintenance and operations systems; includes completed parameters and attributes as specified by SI.
LOD 510, 520, 530, 540 | LOD 510, LOD 520, LOD 530, and LOD 540 models will contain LOD 100, LOD 200, LOD 300, LOD 400 facility and geometry data respectively and will be configured to contain the Operations and Maintenance manuals, warranty information, submittal information, and/or any other documents as applicable or required.
Other: | Narratives, drawings, hand built models, etc.
Please refer to the project specific BIM Plan or the OPP Bim Standards & Guidelines for the level of development required for each model element. Typically any project element under X Inches in size will not be modeled. All elements above X inches should be included in the design model as an "object" unless otherwise specified below.
Each project stakeholder should review, comment, and confirm work efforts and LOD. If an effort has been misassigned, omitted, duplicated, or incorrectly included, please notify the BIM Manager immediately.
Stages (OmniClass Table 31) |  |  | Disciplines (OmniClass Table 33)
10 | Conception Stage |  | 11 | Planning
15 | Project Delivery Selection Stage |  | 21 | Design
20 | Design Stage |  | 25 | Project Management
25 | Construction Documents Stage |  | 31 | Surveying
30 | Procurement Stage |  | 41 | Construction
40 | Execution Stage |  | 55 | Facility Use Disciplines
50 | Utilization Stage |  | 81 | Support Disciplines
60 | Closure Stage |  | 99 | Other Disciplines
for more detail see Disciplines Tab
Based on OmniClass Table 21 Elements (2011-02-11)
Model Element Author
Abbreviaton | Firm/Role | Discipline
PD |  | Prime Designer
DC |  | Design Consultants
PC |  | Prime Constructor
TC |  | Trade Contractors
S |  | Suppliers

## BIM Model Content LOD
Project Stage |  |  | Design Model |  |  |  | Design Intent Model | [6 empty] | Means and Methods Model | [5 empty] | Integration with SI
Time of Exchange (SD, DD, CD, Construction)
Responsible Party (Information Receiver)
Receiver File Format
Application & Version
BIM Use Title |  |  | Model Element (3D) | Model Element (2D) | Data Only (Specs) | Existing Conditions |  | Schematic Design |  | Design Development |  | Construction Documents |  | Shop Drawings |  | Construction Adminstration |  | As-Built Model |  | Record Model |  | O&M Criteria
|  |  | Yes (Y) / No (N) |  |  | Level of Development (LOD) and Model Element Author (MEA)
Model Element (ASTM Uniformat II) Classification |  |  | Y/N | Y/N | Y/N | LOD | MEA | LOD | MEA | LOD | MEA | LOD | MEA | LOD | MEA | LOD | MEA | LOD | MEA | LOD | MEA
A | SUBSTRUCTURE
| A1010 | Standard Foundations
Wall & Column Foundations
Foundation Walls
Grade Beams
Pile Caps
Excavation, Backfill & Compaction
Footings & Bases
Perimeter Insulation
Perimeter Drainage
Anchor Plates/Bolt Patterns
Means & Methods (Erection/Sequencing/ Shop Standards)
| A1020 | Special Foundations
Pile Foundations
Grade Beams
Caissons
Underpinning
Dewatering
Raft Foundations
Pressure Injected Grouting
Other Special Conditions
Means & Methods (Erection/Sequencing/ Shop Standards)
| A1030 | Slab in Grade
Standard Slab on Grade
Structural Slab on Grade
Inclined Slab on Grade
Trenches, Pits, and Bases
Under-Slab Drainage and Insulation
Means & Methods (Erection/Sequencing/ Shop Standards)
| A2010 | Basement Excavation
Excavation for Basements
Structure Back Fill and Compaction
Shoring
Means & Methods (Erection/Sequencing/ Shop Standards)
| A2020 | Basement Walls
Basement Wall Construction
Moisture Protection
Basement Wall Insulation
Interior Skin
Means & Methods (Erection/Sequencing/ Shop Standards
B | SHELL
| B1010 | Floor Construction
Suspended Basement Floors Construction
Upper Floors Construction
Balcony Floors Construction
Ramps
Exterior Stairs and Fire Escapes
Floor Raceway Systems
Other Floor Construction
Means & Methods (Erection/Sequencing/ Shop Standards)
| B1020 | Roof Construction
Flat Roof Construction
Pitched Roof Construction
Canopies
Other Roof Systems
Means & Methods (Erection/Sequencing/ Shop Standards)
| B2010 | Exterior Walls
Exterior Wall Construction
Parapets
Exterior Louvers, Screens, and Facing
Exterior Sun Control Devices
Balcony Walls and Handrails
Exterior Soffits
Means & Methods (Erection/Sequencing/ Shop Standards)
| B2020 | Exterior Windows
Windows
Curtain Walls
Storefronts
Means & Methods (Erection/Sequencing/ Shop Standards)
| B2030 | Exterior Doors
Glazed Doors and Entrances
Solid Exterior Doors
Revolving Doors
Overhead Doors
Personnel Doors
Other Doors and Entrances
Means & Methods (Erection/Sequencing/ Shop Standards)
| B3010 | Roof Coverings
Roof Finishes
Traffic Toppings and Paving Membranes
Roof Insulation and Fill
Flashings and Trim
Copings
Roof Eaves and Soffits
Gutters and Downspouts
Means & Methods (Erection/Sequencing/ Shop Standards)
| B3020 | Roof Openings
Skylights and Glazing
Roof Hatches
Vents
Means & Methods (Erection/Sequencing/ Shop Standards)
C | INTERIORS
| C1010 | Partitions
Fixed Partitions
Demountable Partitions
Retractable Partitions
Site Built Toilet Partitions
Site Built Compartments Cubicles
Interior Balustrades and Screens
Interior Windows and Storefronts
Means & Methods (Erection/Sequencing/ Shop Standards)
| C1020 | Interior Doors
Interior Doors
Interior Door Frames
Interior Door Hardware
Interior Door Wall Opening Elements
Interior Door Sidelights and Transoms
Interior Hatch and Access Doors
Door Painting and Decoration
Means & Methods (Erection/Sequencing/ Shop Standards)
| C1030 | Fittings
Fabricated Toilet Partitions
Fabricated Compartments and Cubicles
Storage Shelving and Lockers
Ornamental Metals and Handrails
Identifying Devices
Closet Specialties
General Fittings and Misc. Metals
Means & Methods (Erection/Sequencing/ Shop Standards)
| C2010 | Stair Construction
Stair Treads, Risers, & Landings
Stair Handrails and Balustrades
Means & Methods (Erection/Sequencing/ Shop Standards)
| C2020 | Stair Finishes
Stair, Tread, Landing Finishes
Stair Soffit Finishes
Stair Handrail and Balustrade Finishes
| C3010 | Wall Finishes
Wall Finishes to Inside Exterior Walls
Wall Finishes to Inside Walls
Column Finishes
Other
| C3020 | Floor Finishes
Floor Toppings
Traffic Membranes
Hardeners and Sealers
Flooring
Carpeting
Bases, Curbs, Trim
Access Pedastal Flooring
Other
| C3030 | Ceiling Finishes
Ceiling Finishes
Suspended Ceilings
Trim and Decoration
Other Ceilings
D | SERVICES
| D1010 | Elevators & Lifts
Passenger Elevators
Freight Elevators
People Lifts
Wheelchair Lifts
Means & Methods (Erection/Sequencing/ Shop Standards)
| D1020 | Escalators & Moving Walks
Escalators
Moving Walks
Means & Methods (Erection/Sequencing/ Shop Standards)
| D1030 | Other Conveying Systems
Dumbwaiters
Pneumatic Tube Systems
Hoists and Cranes
Conveyors
Chutes
Turntables
Baggage Handling and Loading Systems
Transportation Systems
Means & Methods (Erection/Sequencing/ Shop Standards)
| D2010 | Plumbing Fixtures
Water Closets
Urinals
Lavatories
Sinks
Bathtubs
Wash Fountains
Showers
Drinking Fountains and Coolers
Bidets and Other Plumbing Fixtures
Means & Methods (Erection/Sequencing/ Shop Standards)
| D2010 | Domestic Water Distribution
Cold Water Service
Hot Water Service
Pipes & Fittings
Valves, Hydrants, & Hose Bibbs
Water Heater
Domestic Water Supply Equipment
Insulation
Means & Methods (Erection/Sequencing/ Shop Standards)
| D2030 | Sanitary Waste
Waste Piping & Fittings
Vent Piping & Fittings
Floor Drains
Sanitary Waste Equipment
Pipe Insulation
Means & Methods (Erection/Sequencing/ Shop Standards)
| D2040 | Rain Water Drainage
Pipe and Fittings
Roof Drains
Cistern
Filtration
Other Rainwater Drainage Equipment
Pipe Insulation
Means & Methods (Erection/Sequencing/ Shop Standards)
| D2090 | Other Plumbing Systems
Gas Distribution
Acid Waste Systems
Interceptors
Pool Piping and Equipment
Decorative Fountain Piping Devices
Other Piping Systems
Means & Methods (Erection/Sequencing/ Shop Standards)
| D3010 | Energy Supply
Oil Supply System
Gas Supply System
Coal Supply System
Steam Supply System
Hot Water Supply System
Solar Energy System
Wind Energy System
Means & Methods (Erection/Sequencing/ Shop Standards)
| D3020 | Heat Generating Systems
Boilers
Boiler Room Piping and Specialties
Auxilary Equipment
Insulation
Means & Methods (Erection/Sequencing/ Shop Standards)
| D3030 | Cooling Generating Systems
Chillers
Cooling Towers and Evaporative Coolers
Condensing Units
Pipes & Fittings
Primary Pumps
Auxillary Equipment
Insulation
Means & Methods (Erection/Sequencing/ Shop Standards)
| D3040 | Distribution Systems
Supply & Return Air Systems
AHU w/coils, ducts, and devices
Vent & Exhaust Systems
Steam, Hydronic, Hot Water, Glycol & Chilled Water Distribution
Heat Recovery Equipment
Auxillary Equipment
Insulation
Means & Methods (Erection/Sequencing/ Shop Standards)
| D3050 | Terminal & Package Units
Terminal Self-Contained Units
Package Units
Other
Means & Methods (Erection/Sequencing/ Shop Standards)
| D3060 | Controls & Instrumentation
Heating Generating Systems
Cooling Generating Systems
Heating/Cooling Air Handling Units
Exhausts and Ventilating Systems
Hoods and Exhaust Systems
Terminal Devices
Energy Monitoring and Control
Building Automation Systems
Other Controls and Instrumentation
Means & Methods (Erection/Sequencing/ Shop Standards)
| D3070 | Systems Testing & Balancing
Commissioing Cx
| D3090 | Other HVAC Systems & Equipment
Special Cooling Systems and Devices
Special Humidity Control
Dust and Fume Collectors
Air Curtains
Air Purifiers
Paint Spray Booth Ventilation
General Construction Items (HVAC)
Means & Methods (Erection/Sequencing/ Shop Standards)
| D4010 | Sprinklers
Sprinkler Water Supply
Sprinkler Pumping Equipment
Dry Sprinkler System
Means & Methods (Erection/Sequencing/ Shop Standards)
| D4020 | Standpipes
Standpipe Water Supply
Pumping Equipment
Standpipe Equipment
Fire Hose Equipment
Means & Methods (Erection/Sequencing/ Shop Standards)
| D4030 | Fire Protection Specialties
Fire Extinguishers
Fire Extinguisher Cabinets
Means & Methods (Erection/Sequencing/ Shop Standards)
| D4090 | Other Fire Protection Systems
Carbon Dioxide Systems
Ammonia Systems
Foam Generating Equipment
Clean Agent Systems
Dry Chemical System
Hood and Duct Fire Protection
Fire Alarm
Means & Methods (Erection/Sequencing/ Shop Standards)
| D5010 | Electrical Service & Distribution
Primary Transformers
Secondary Transformers
Main Switchboard
Interior Distribution Transformer
Branch Circuit Panels
Motor Control Center
Conduit & Wiring to Circuit Panels
Means & Methods (Erection/Sequencing/ Shop Standards)
| D5020 | Lighting & Branch Wiring
Lighting Fixtures
Devices
Exterior Building Lighting
Means & Methods (Erection/Sequencing/ Shop Standards)
| D5030 | Communication and Security
Fire Alarm System
Intercom System
Tele-Data System
Access Control
Panic-Emergency Call Devices
Security Syste,/Cameras
Means & Methods (Erection/Sequencing/ Shop Standards)
| D5090 | Other Electrical Systems
Grounding Systems
Emergency Light and Power Systems
Floor Raceway Systems
Other Special Systems and Devices
General Construction Items (Elect)
Means & Methods (Erection/Sequencing/ Shop Standards)
E | EQUPMENT AND FURNISHINGS
| E1010 | Commercial Equipment
Security and Vault Equipment
Teller and Service Equipment
Registration Equipment
Checkroom Equipment
Mercantile Equipment
Laundry and Dry Cleaning Equipment
Vending Equipment
Office Equipment
Means & Methods (Erection/Sequencing/ Shop Standards)
| E1020 | Institutional Equipment
Ecclesiastical Equipment
Library Equipment
Theater and Stage Equipment
Instrumental Equipment
Audio-visual Equipment
Detention Equipment
Laboratory Equipment
Medical Equipment
Other Instrumentational Equipment
Means & Methods (Erection/Sequencing/ Shop Standards)
| E1030 | Vehicular Equipment
Vehicular Service Equipment
Parking Control Equipment
Loading dock Equipment
Other Vehicular Equipment
| E1090 | Other Equipment
Maintenance Equipment
Solid Waste Handling Equipment
Food Service Equipment
Residential Equipment
Unit Kitchens
Window Washing equipment
Other Equipment
Means & Methods (Erection/Sequencing/ Shop Standards)
| E2010 | Fixed Furnishings
Fixed Artwork
Fixed Casework
Blinds and Other Window Treatment
Fixed Floor Grilles and Mats
Fixed Multiple Seating
Fixed Interior Landscaping
Other
| E2020 | Movable Furnishings
Movable Artwork
Furniture and Accessories / Fitness Equipment
Movable Rugs and Mats
Movable Interior Landscaping
Other
F | SPECIAL CONSTRUCATION AND DEMOLITION
| F1010 | Special Structure
Air Supported Structures
Pre-engineered Structures
Other Special Structures
Means & Methods (Erection/Sequencing/ Shop Standards)
| F1020 | Integrated Construction
Integrated Assemblies
Special Purpose Rooms
Clean Rooms
Other Integrated Construction
Means & Methods (Erection/Sequencing/ Shop Standards)
| F1030 | Special Construction Systems
Sound, Vibration, Seismic Const.
Radiation Protection
Special Security Systems
Vaults
Other Special Construction Systems
Means & Methods (Erection/Sequencing/ Shop Standards)
| F1040 | Systems for Special Facilities
Aquatic Facilities
Ice Rinks
Site Constructed Incinerators
Kennels and Animal Shelters
Liquid Gas and Storage Tanks
Other Special Facilities
Means & Methods (Erection/Sequencing/ Shop Standards)
| F1050 | Special Controls & Instrumentation
Recording Instrumentation
Building Automation Systems
Other Special Controls and Instrum.
Means & Methods (Erection/Sequencing/ Shop Standards)
| F2010 | Building Elements Demolition
Building Elements Demolition
Hazardous Components Abatement
Means & Methods (Erection/Sequencing/ Shop Standards)
G | SITEWORK
| G1010 | Site Clearing
Site Clearing
Means & Methods (Erection/Sequencing/ Shop Standards)
| G1020 | Site Demolition & Relocations
Site Demolition
Relocation of Building Utilities
Means & Methods (Erection/Sequencing/ Shop Standards)
| G1030 | Site Earthwork
Shoring Walls
Site/Topography
Means & Methods (Erection/Sequencing/ Shop Standards)
| G1040 | Hazardous Waste Remediation
Waste Remediation
Means & Methods (Erection/Sequencing/ Shop Standards)
| G2010 | Roadways
Paving & Surface
Curbs & Gutters
Rails & Barriers
Markings & Signage
Means & Methods (Erection/Sequencing/ Shop Standards)
| G2020 | Parking Lots
Parking Lot Paving
Curbs, Rails, & Barriers
Parking Booths & Equipment
Markings & Signage
Means & Methods (Erection/Sequencing/ Shop Standards)
| G2030 | Pedestrian Paving
Pavers
Exterior Steps
Means & Methods (Erection/Sequencing/ Shop Standards)
| G2040 | Site Devlopment
Fences & Gates
Retaining Walls
Terrace & Perimeter Walls
Signage
Fountains & Pools
Playing Fields
Flag Poles
Other
Means & Methods (Erection/Sequencing/ Shop Standards)
| G2050 | Landscaping
Trees & Bushes
Means & Methods (Erection/Sequencing/ Shop Standards)
| G3010 | Water Supply & Distibution Systems
Potable & Nonpotable Water Systems
Pumping Stations
Water Storage
Means & Methods (Erection/Sequencing/ Shop Standards)
| G3020 | Sanitary Sewer Systems
Piping
Manholes
Septic Tanks
Catch Basins
Package Waste Water Treatment Plants
Means & Methods (Erection/Sequencing/ Shop Standards)
| G3030 | Storm Sewer Systems
Piping
Manholes
Catch Basins
Retention Ponds
Ditches & Culverts
Means & Methods (Erection/Sequencing/ Shop Standards)
| G3040 | Heating Distribution
Steam Supply System
Condensation Return
Hot Water Supply System
Means & Methods (Erection/Sequencing/ Shop Standards)
| G3050 | Cooling Distribution
Chilled Water Piping
Pumping Stations
Cooling Towers on Site
Means & Methods (Erection/Sequencing/ Shop Standards)
| G3060 | Fuel Distribution
Piping
Equipment
Storage Tanks
Means & Methods (Erection/Sequencing/ Shop Standards)
| G3090 | Other Civil/Mechanical Utilities
Industrial Waste Systems
Petroleum & Lubricant Distribution System
Means & Methods (Erection/Sequencing/ Shop Standards)
| G4010 | Electrical Distribution
Substations
Overhead & Underground Power Distribution
Duct Banks
Means & Methods (Erection/Sequencing/ Shop Standards)
| G4020 | Site Lighting
Fixtures & Transformers
Poles
Conduit & Duct Banks
Means & Methods (Erection/Sequencing/ Shop Standards)
| G4030 | Site Communications & Security
Special Communications
Site Security
Means & Methods (Erection/Sequencing/ Shop Standards)
| G4090 | Other Electrical Utilities
Special Electrical Utilities
Means & Methods (Erection/Sequencing/ Shop Standards)
| G5010 | Service Tunnels
Conduit & Duct Banks
Means & Methods (Erection/Sequencing/ Shop Standards)
| G5090 | Other Site Systems & Equipment
Equipment
Means & Methods (Erection/Sequencing/ Shop Standards)
Designated Design/Performance Specifications
This section takes precedence over representations above in case there is duplication,
Design Construction/ Performance Specifications
This section takes precedence over representations above in case there is duplication,
* | Additional Information
| 1 | Construction Systems
Construction Equipment
Temporary Safety
Temporary Security
Temporary Facilities
Weather Protection
| 2 | Space
Construction Activity Space
Analysis Space
| 3 | Information
Construction Information
Engineering Information
Record Information
| 4 | Datum
Grid
Levels
Origin
Additional
ALL EXISTING CONDITIONS TO BE MODELED TO A 200 LEVEL UNLESS DIRECTLY AFFECTED BY NEW CONSTRUCTION. THEN MODELED/DETAILED TO A 300 LEVEL TO ALLOW FOR DEMOLITION DRAWINGS AND TIE IN INFORMATION

## Disciplines
| Disciplines (OmniClass Table 33) |  |  |  |  | Responsible Party
33 | 11 | Planning
33 | 11 | 11 | Regional Planning
33 | 11 | 21 | Development Planning
33 | 11 | 31 | Rural Planning
33 | 11 | 41 | Urban Planning
33 | 11 | 44 | Transportation Planning
33 | 11 | 51 | Enviromental Planning
33 | 11 | 61 | Facility Conservation Planning
33 | 11 | 99 | Other Planning
33 | 21 | Design
33 | 21 | 11 | Architecture
33 | 21 | 19 | Drafting
33 | 21 | 21 | Landscape Architecture
33 | 21 | 23 | Interior Design
33 | 21 | 25 | Specifying
33 | 21 | 27 | Graphic Design
33 | 21 | 31 | Engineering
33 | 21 | 31 | 11 | Civil Engineering
33 | 21 | 31 | 14 | Sructural Engineering
33 | 21 | 31 | 17 | Mechanical Engineering
33 | 21 | 31 | 21 | Electrical Engineering
33 | 21 | 31 | 23 | Communications Engineering
33 | 21 | 31 | 24 | Process Engineering
33 | 21 | 31 | 27 | Military Engineering
33 | 21 | 31 | 99 | Other Engineering
33 | 25 | Project Management
33 | 21 | 11 | Cost Estimation
33 | 21 | 14 | Proposal Preparation
33 | 21 | 17 | Client Briefing
33 | 21 | 21 | Scheduling
33 | 21 | 31 | Contract Adminstration
33 | 21 | 41 | Procurement
33 | 21 | 51 | Quality Assurance
33 | 21 | 54 | Quality Control
33 | 31 | Surveying
33 | 31 | 11 | Building Surveying
33 | 31 | 21 | Site Surveying
33 | 31 | 31 | GIS (Geographical Information Sytem) Engineering
33 | 41 | Construction
33 | 41 | 11 | Contracting
33 | 41 | 11 | 11 | General Contracting
33 | 41 | 11 | 14 | Subcontracting
33 | 41 | 11 | 14 | 11 | Masonry
33 | 41 | 11 | 14 | 14 | Carpentry
33 | 41 | 11 | 14 | 17 | Iron Working
33 | 41 | 11 | 14 | 21 | Plumbing Subcontracting
33 | 41 | 11 | 14 | 24 | Fire Protection Subcontracting
33 | 41 | 11 | 14 | 27 | Heating Ventilation and Air Conditioning Subcontracting
33 | 41 | 11 | 14 | 28 | Refrigeration Subcontracting
33 | 41 | 11 | 14 | 37 | Electrical Subcontracting
33 | 41 | 11 | 14 | 51 | Energy Monitoring and Controls Subcontracting
33 | 41 | 11 | 14 | 54 | Hydrological Subcontracting
33 | 41 | 11 | 14 | 61 | Painting
33 | 41 | 11 | 14 | 64 | Tiling
33 | 41 | 11 | 14 | 66 | Plaster Subcontracting
33 | 41 | 11 | 14 | 63 | Gypsum Board Subcontracting
33 | 41 | 14 | Construction Management
33 | 55 | Facility Use Disciplines
33 | 55 | 14 | Real Estate
33 | 55 | 21 | Owner
33 | 55 | 24 | Facility Operations
33 | 55 | 36 | Facility Resoration
33 | 81 | Support Disciplines
33 | 81 | 11 | Legal
33 | 81 | 13 | Environment
33 |  | 31 | Finance
33 | 81 | 34 | Human Resources
33 | 99 | Other Disciplines
33 | 99 | 11 | Science
33 | 99 | 13 | Art
33 | 99 | 41 | Security
33 | 99 | 45 | Public Relations
33 | 99 | 61 | Education