## Sheet1
| Discipline: | ARCHITECTURE |  |  |  |  | MECH/ELEC/PLUMB/FP | [6 empty] | STRUCTURAL |  |  | CIVIL |  | COST |  | Other
TASKS & Subtasks (per SOW) | T1 or NT1 | Principal | Project Manager | Project Architect | Sr. Architect | Jr. Architect / CADD | Principal | Sr. Mech. Engineer | Jr. Mech. Engineer | Sr. Elec. Engineer | Plumbing/FP Engineer | Draftsperson / CADD | Spec Writer | Principal | Structural Engineer | Draftsperson / CADD | Principal | Civil Engineer | Sr. Estimator | Estimator | Lighting Consultant
SCHEMATICS
Prepare Schematic Report | NT1
Prepare Schematic Drawings | NT1
Prepare model | NT1
Attend Schematic Presentation | NT1
TOTAL SCHEMATICS (NON-TITLE 1) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DESIGN DEVELOPMENT
Prepare 35% drawings | NT1
Prepare 35% outline specs | NT1
Prepare 35% cost estimate | NT1
Attend and prepare for meetings, follow up | NT1
Prepare responses to 35% comments | NT1
Prepare for and attend NCPC presentation | NT1
TOTAL DESIGN DEVELOPMENT (NON-TITLE 1) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONSTRUCTION DOCUMENTS
Prepare 65% drawings | T1
Prepare 65% specs | T1
Prepare 65% cost estimate | T1
Prepare 65% construction schedule | T1
Prepare responses to 65% comments | T1
Prepare 95% drawings | T1
Prepare 95% specs | T1
Prepare 95% cost estimate | T1
Prepare 95% construction schedule | T1
Prepare responses to 95% comments | T1
Prepare 100% drawings | T1
Prepare 100% specs | T1
Prepare 100% cost estimate | T1
Prepare 100% construction schedule | T1
Attend and prepare for meetings | NT1
Prepare & submit construction schedule | NT1
TOTAL CONSTRUCTION DOCUMENTS | TITLE 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| NON-TITLE 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0